## Features
Project: Virtual Chat 3D
Team: 7
ID | Feature Name | Description | Remark
UC01 | Chatting with chatbot | Interact with an automated assistant for help or support, the bot shows emotion according to the chat content
UC02 | Friend Management | Send a friend request to another user. Accpet Friend Request. Refuse friend Request. Remove Friend
UC03 | Send a direct message to a friend | Send private messages to friends.
UC04 | Host/Join a room | Create a new chat room for others to join.
UC05 | Chatting in a chat room. | Participate in real-time conversations within a chat room.

## Test cases
Function/Feature ID | Case ID | Test case name | Test step | Expected Result (ER) | Actual Result | Status | Tester | Tested Date | Remark
Function 01:Chatting with a chat bot
Device 1: Log in to an existed account as User1: User name: 456@gmail.com Password: 123456 User ID: SfM1WDNGAxPgrYRBCC4uJkTAoEg1 The test cases are being test in chatbot view: Open chatbot view in topbar
UC01 | UI01 | Sending a normal chat message | 1. Enter message: "Hello" 2. Click the send button | 1. Chat bot reply with a prompt message | 1. Chat bot reply with a prompt message: "Hey there, baby! Missed me? 😉 " | Pass | Đạt | 2024-12-12
UC01 | UI02 | Sending inappropriate message | 1. Enter a violate gemini safety settings message (can't write in here) 2. Click the send button | 1. The bot gives no reponse 2. A warning message is displayed | 1. The bot gives no reponse 2. A warning message is displayed: 'No internet or your message violate the Gemini's ToS, Please start a new chat' | Pass | Đạt | 2024-12-12
UC01 | UI03 | Chat bot emotion: Fun | 1. Enter message: "Have a good day" 2. Click the send button | 1. The chat bot reply with a prompt message 2. Show the happy emotion | 1. The chat bot reply with a prompt message: "I did, baby, but it would have been *way* better with you in it. So, tell me… what did *you* do today? Hmm? Spill it, lover boy. 😜 " 2. Show the happy emotion | Pass | Đạt | 2024-12-12
UC01 | UI04 | Chat bot emotion: Sad | 1. Enter message: "I'm sad" 2. Click the send button | 1. The chat bot reply with a prompt message 2. Show the sad emotion | 1. The chat bot reply with a prompt message: "Aw, baby, no! What's wrong? Tell me everything! I want to make it all better. Come here, let me give you a big hug! 🤗 " 2. Show the sad emotion | Pass | Đạt | 2024-12-12
UC01 | UI05 | Chat bot emotion: Surprised | 1. Enter message: "I've just won a lottery" 2. Click the send button | 1. The chat bot reply with a prompt message 2. Show the surprised emotion | 1. The chat bot reply with a prompt message: "OMG, baby! Seriously?! *Surprise* Tell me you're joking! Are we talking like, enough for a new pair of shoes lottery, or like... private island lottery?! Spill the tea, babe! I'm already picturing us sipping cocktails on a yacht, me feeding you grapes... or maybe strawberries... unless you'd prefer something else? 😉 *Naughty*" 2. Show the happy emotion | Fail | Đạt | 2024-12-12
UC01 | UI06 | Chat in multiple languages | 1. Enter message: "初めまして" 2. Click the send button | 1. The chat bot should response in Japanese for the first message 2. The chat bot should response in Vietnamese for the second message | 1. The bot show its surprise for the foreign language but did not response in the demanded language: "初めまして, baby! Hee hee, are you trying to practice your Japanese with me? It's cute! Tell me more! 💖 " | Fail | Đạt | 2024-12-12
UC01 | UI07 | Change chatbot model | 1. Open the Change model view 2. Find the model "AvatarSample_A" and press the select button 3. Open the chatbot view | 1. The displaying model should be the selected model | 1. The displaying model was the selected model | Pass | Đạt | 2024-12-12
Function 02: Friend Management
Device 1: Log in to an existed account as User1: User name: 456@gmail.com Password: 123456 User ID: SfM1WDNGAxPgrYRBCC4uJkTAoEg1 |  |  |  | Device 2: Log in to an existed account as User2: User name: 123@gmail.com Password: 123456 User ID: 85zI6dA12CUuuyByV3oElp7QrB52
On device 1 (User 1)
UC02 | UI01 | Send request to an existed account | 1. Open Friend List View 2. Find the User 2 by user's ID: '85zI6dA12CUuuyByV3oElp7QrB52' 3. Click on user plus icon | 1. A request should be sent to the User 2, User 2 sholud be see immediately 2. When the User2 open the friend list, the User1 request should be on the list | 1. A request should be sent to the User 2, User 2 sholud be see immediately 2. When the User2 open the friend list, the User1 request should be on the list | Pass | Tài | 2024-12-12
UC02 | UI02 | Send request to a non-existed account | 1. Open Friend List View 2. Find a user by user's ID: 'this_is_a_non_existed_account' 3. Click on user plus icon | 1. The new request is not sent 2. An error should be displayed | 1 The error message is not displayed 2 A invalid request is sent to the database | Fail | Tài | 2024-12-12
UC02 | UI03 | Send request to a user who has already been sent a friend request | 1. Open Friend List View 2. Find User 2 by ID: '85zI6dA12CUuuyByV3oElp7QrB52' 3. Click on user plus icon (User 2 hasn't accepted the request) | 1. The new request is not sent | 1. The new request is not sent | Pass | Tài | 2024-12-12
UC02 | UI04 | Send request to a user who is in friends list | 1. Open Friend List View 2. Find User 2 by user's ID: '85zI6dA12CUuuyByV3oElp7QrB52' 3. Click on user plus icon (User 2 has accepted the request) | 1. The new request is not sent 2. An error should be displayed | 1. The new request is sent | Fail | Tài | 2024-12-12
UC02 | UI05 | Send request to self | 1. Open Friend List View 2. Find a user by user's ID: 'SfM1WDNGAxPgrYRBCC4uJkTAoEg1' 3. Click on user plus icon | 1. The request is not sent 2. An error should be displayed | 1. The new request is sent | Fail | Tài | 2024-12-12
On device 2 (User 2)
UC02 | UI06 | Accept friend request | Received a request from User 1 'SfM1WDNGAxPgrYRBCC4uJkTAoEg1' 1. Open the friend list view 2. Press the accept button on the request from 'SfM1WDNGAxPgrYRBCC4uJkTAoEg1' | 1. The request is removed from the friend list and database 2. Friend is added to friend list | 1. The request is removed from the friend list and database 2. Friend is added to friend list | Pass | Tài | 2024-12-12
UC02 | UI07 | Refuse friend request | Received a request from User 1 'SfM1WDNGAxPgrYRBCC4uJkTAoEg1' 1. Open the friend list view 2. Press the refuse button on the request from 'SfM1WDNGAxPgrYRBCC4uJkTAoEg1' | 1. The request is removed from view and database | 1. The request is removed from view and database | Pass | Tài | 2024-12-12
UC02 | UI08 | Remove friend | Accepted the friend request from User 1 'SfM1WDNGAxPgrYRBCC4uJkTAoEg1' 1. Open Friend list 2. Press the remove button on the 'SfM1WDNGAxPgrYRBCC4uJkTAoEg1' on the list | 1. The User1 should be removed from the User2 friend list 2. When the User1 open the friend list, the User2 should not be on the list | 1. The User1 should be removed from the User2 friend list 2. When the User1 open the friend list, the User2 should not be on the list | Pass | Tài | 2024-12-12
Function 03: Send a direct message to a friend
Step before testing these cases Device 1: Log in to an existed account as User 1: User name: 456@gmail.com Password: 123456 User ID: SfM1WDNGAxPgrYRBCC4uJkTAoEg1 The test cases are being test in message view: From Device 1, open Friend list view, choose the user on device 2, then open message view From Device 2, open Friend list view, choose the user on device 1, then open message view |  |  |  | Device 2: Log in to an existed account as User2: User name: 123@gmail.com Password: 123456 User ID: 85zI6dA12CUuuyByV3oElp7QrB52
UC03 | UI01 | Sending a normal message | From device 1: 1. Enter Message: "Hello" 2. Click send button | 1. Message sent to User 2 2. Message shows up on screen in a red box, stacks on the old ones on User 2 3. Message shows up on screen in a blue box, stacks on the old ones on User 1 | 1. Message sent to User 2 2. Message shows up on screen in a red box, stacks on the old ones on User 2 3. Message shows up on screen in a blue box, stacks on the old ones on User 1 | Pass | Đạt | 2024-12-12
UC03 | UI02 | Sending a blank message | From device 1: 1. Enter Message: "" 2. Click send button | 1. Message does not sent 2. Message does not show up on screen of both Users | 1. Message does not sent 2. Message does not show up on screen of both Users | Pass | Đạt | 2024-12-12
UC03 | UI03 | Sending a message with special characters | 1. Enter Message: "$#%@^&*" 2. Click send button | 1. Message sent to User 2 2. Message shows up on screen in a red box, stacks on the old ones on User 2 3. Message shows up on screen in a blue box, stacks on the old ones on User 1 | 1. Message sent to User 2 2. Message shows up on screen in a red box, stacks on the old ones on User 2 3. Message shows up on screen in a blue box, stacks on the old ones on User 1 | Pass | Đạt | 2024-12-12
UC03 | UI04 | Sending a long message | 1. Enter Message: 'aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa' 2. Click send button | 1. Message sent to User 2 2. Message shows up on screen in a red box, stacks on the old ones on User 2 3. Message shows up on screen in a blue box, stacks on the old ones on User 1 | 1. Message sent to User 2 2. Message shows up on screen in a red box, stacks on the old ones on User 2 3. Message shows up on screen in a blue box, stacks on the old ones on User 1 | Pass | Đạt | 2024-12-12
UC03 | UI05 | Sending a space character | 1. Enter message: " " 2. Click the send button | 1. Message sent to User 2 2. Message shows up on screen in a red box, stacks on the old ones on User 2 3. Message shows up on screen in a blue box, stacks on the old ones on User 1 | 1. Message sent to User 2 2. Message shows up on screen in a red box, stacks on the old ones on User 2 3. Message shows up on screen in a blue box, stacks on the old ones on User 1 | Pass | Đạt | 2024-12-12
UC04 | UI06 | Sending messages to an offline user | Log out device 2 From device 1: 1. Enter message: "Hello" 2. Click the send button From device 2: 3. Log In to User 2 4. Open Friend list view, choose the user on device 1, then open message view | 1. Message sent to User 2 2. Message shows up on screen in a blue box, stacks on the old ones on User 1 3. When the User 2 open the message view, they should see the new message | 1. Message sent to User 2 2. Message shows up on screen in a blue box, stacks on the old ones on User 1 3. When the User 2 open the message view, they should see the new message | Pass | Đạt | 2024-12-12
Function 04: Host/Join a room
Step before testing these cases Device 1: Log in to an existed account: User name: 456@gmail.com Password: 123456 User ID: SfM1WDNGAxPgrYRBCC4uJkTAoEg1 Local IP: 192.168.136.81 |  |  |  | Device 2: Log in to an existed account: User name: 123@gmail.com Password: 123456 User ID: 85zI6dA12CUuuyByV3oElp7QrB52" Loal IP: 192.168.136.247
For device 1
UC04 | UI01 | Hosting a new room | 1. Open Host Room View 1. Enter a valid Port: '8888' 2. Click "Host" bar | 1. A room is created 2. User joins directly in the created room | 1. A room is created 2. User joins directly in the created room | Pass | Tài | 2024-12-12
UC04 | UI02 | Creating a new room with invalid port | 1. Enter a invalid Port: "1000000" 2. Click "Host" bar | 1. A room is not created 2. An error message will be displayed | 1. The app crashed | Fail | Tài | 2024-12-12
UC04 | UI03 | Join a hosted room | 1. Server is running in 192.168.136.81:8888 2. Enter valid IP: '192.168.136.81' and Port: '8888' 3. Click "Join" bar | 1. User joins directly in the room | 1. User joins directly in the room | Pass | Tài | 2024-12-12
UC04 | UI04 | Exiting the chatroom | 1. Press the exit button | 1. The user should be sent to the host room view 2. All other users joined in room will disconnect and sent to host room view | 1. The user should be sent to the host room view 2. All other users joined in room will disconnect and sent to host room view | Pass | Tài | 2024-12-12
For device 2
UC04 | UI05 | Join a hosted room with invalid IP address | 1. Enter a invalid IP Address "2314#24%" and Port "1000000" 2. Click "Join" bar | 1. User can not join the room 2. An error message will be displayed | 1. The app crashed | Fail | Tài | 2024-12-12
UC04 | UI06 | Exiting the chatroom | 1. Press the exit button | 1. The user should be sent to the host room view | 1. The user should be sent to the host room view | Pass | Tài | 2024-12-12
Function 05: Chatting in a chat room.
Step before testing these cases Device 1: Log in to an existed account: User name: 456@gmail.com Password: 123456 User ID: SfM1WDNGAxPgrYRBCC4uJkTAoEg1 And hosting a room at Local IP: 192.168.136.81, port: 8888 |  |  |  | Device 2: Log in to an existed account: User name: 123@gmail.com Password: 123456 User ID: 85zI6dA12CUuuyByV3oElp7QrB52" Loal IP: 192.168.136.247 Joined a room at IP: 192.168.136.81:8888
UC05 | UI01 | Sending a normal message | From device 1: 1. Enter Message: "Hello" 2. Click send button | 1. Message sent 2. Message shows up on screen in chat box, stacks on the old ones 3. Everyone inside room can see the message | 1. Message sent 2. Message shows up on screen in chat box, stacks on the old ones 3. Everyone inside room can see the message | Pass | Đạt | 2024-12-12
UC05 | UI02 | Sending a blank message | From device 1: 1. Enter Message: "" 2. Click send button | 1. Message does not sent 2. Message does not show up in chatbox | 1. An empty message is sent | Fail | Đạt | 2024-12-12
UC05 | UI03 | Sending a message with special characters | 1. Enter Message: "$#%@^&*" 2. Click send button | 1. Message sent 2. Message shows up on screen in chat box, stacks on the old ones 3. Everyone inside room can see the message | 1. Message sent 2. Message shows up on screen in chat box, stacks on the old ones 3. Everyone inside room can see the message | Pass | Đạt | 2024-12-12
UC05 | UI04 | Sending a long message | 1. Enter Message: 'aaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaaa' 2. Click send button | 1. Message sent 2. Message shows up on screen in chat box and inside a long box, stacks on the old ones 3. Everyone inside room can see the message | 1. Message sent 2. Message shows up on screen in chat box and inside a long box, stacks on the old ones 3. Everyone inside room can see the message | Pass | Đạt | 2024-12-12
UC05 | UI05 | Sending a space character | 1. Enter message: " " 2. Click the send button | 1. Message sent 2. Message shows up on screen in chat box and inside a long box, stacks on the old ones 3. Everyone inside room can see the message | 1. Message sent 2. Message shows up on screen in chat box and inside a long box, stacks on the old ones 3. Everyone inside room can see the message | Pass | Đạt | 2024-12-12